## October 15, 2023
Test case plan
2023-10-13
# | Functionality/Characteristics | Scenario | Description | Notes | Tested by | Edge | Firefox | Chrome
1 | Page Load | Page loads | After the HTML file is opened, the page loads properly with all images. |  | Sam | Passed | Passed | Passed
2 | Overall body theme | Styles applied | When the page is loaded, the appropriate styles are applied for the body and general fonts |  | Bob | Passed | Passed | Passed
3 | Donut list | Donut list loads | There is a list of available donuts that includes their names, descriptions, and prices. |  | Bob | Passed | Passed | Failed
4 | Admin page | Admin page works | The donut list can be edited from the admin page.
5 | Database | Database connects | The site can retrieve and edit data from the database.

## October 17, 2023
Test case plan
2023-10-17
# | Functionality/Characteristics | Scenario | Description | Notes | Tested by | Edge | Firefox | Chrome
1 | Page Load | Page loads | After the HTML file is opened, the page loads properly with all images. |  | Sam | Passed | Passed | Passed
2 | Overall body theme | Styles applied | When the page is loaded, the appropriate styles are applied for the body and general fonts |  | Bob | Passed | Passed | Passed
3 | Background image | Styles applied to BG | The page loads the appropriate background image | Corrected problem in Chrome: forgot normalize CSS | Bob | Passed | Passed | Passed